## R1_S3(6)
Group name | Item | Item Summary | Estimation time | Spent time | Abs Err
- | PAR-128 | Github issue: Street Name in report creation | 30 | 30 | 0
- | PAR-129 | Github issue: Better manage of Map borders | 90 | 150 | 0.66667
- | PAR-130 | Github issue: Change the modification layout (no an entire page) | 30 | 30 | 0
- | PAR-131 | Sprint Planning | 720 | 720 | 0
- | PAR-132 | Github issue: Remove button from navbar if not logged in | 30 | 30 | 0
- | PAR-133 | Github issue: Reports filtering | 30 | 30 | 0
- | PAR-134 | Scrum Meeting 1 | 90 | 90 | 0
- | PAR-135 | Scrum Meeting 2 | 90 | 90 | 0
- | PAR-136 | Scrum Meeting 3 | 90 | 90 | 0
- | PAR-137 | Scrum Meeting 4 | 90 | 75 | 0.16667
- | PAR-138 | Code Merge | 435 | 435 | 0
- | PAR-139 | Update OpenAPI Documentation | 360 | 280 | 0.22222
- | PAR-140 | Technical Debt: Code Review | 300 | 300 | 0
- | PAR-141 | Technical Debt: Bug fixing | 300 | 360 | 0.2
- | PAR-142 | Technical Debt: Refactoring | 300 | 270 | 0.1
- | PAR-143 | CI-CD pipeline setup | 120 | 150 | 0.25
- | PAR-144 | DB config | 60 | 60 | 0
- | PAR-145 | Router Management | 60 | 60 | 0
- | PAR-146 | Controller Management | 60 | 60 | 0
- | PAR-147 | UI Implementation | 90 | 90 | 0
- | PAR-148 | E2E testing | 30 | 30 | 0
- | PAR-149 | Integration testing | 60 | 60 | 0
- | PAR-150 | Unit testing | 60 | 60 | 0
- | PAR-151 | Router Management | 90 | 90 | 0
- | PAR-152 | Controller Management | 60 | 60 | 0
- | PAR-153 | UI Implementation | 30 | 30 | 0
- | PAR-154 | Integration testing | 60 | 60 | 0
- | PAR-155 | Unit testing | 45 | 45 | 0
- | PAR-156 | E2E testing | 30 | 30 | 0
- | PAR-157 | DB config | 120 | 90 | 0.25
- | PAR-158 | Router Management | 60 | 50 | 0.16667
- | PAR-159 | Controller Management | 60 | 60 | 0
- | PAR-160 | Socket API Documentation | 120 | 40 | 0.66667
- | PAR-161 | Socket API Implementation | 240 | 60 | 0.75
- | PAR-162 | UI Implementation | 120 | 240 | 1
- | PAR-163 | E2E testing | 60 | 60 | 0
- | PAR-164 | Integration testing | 90 | 90 | 0
- | PAR-165 | Unit testing | 60 | 60 | 0
- | PAR-166 | DB config | 60 | 60 | 0
- | PAR-167 | SMTP config | 30 | 30 | 0
- | PAR-168 | Router Management | 60 | 60 | 0
- | PAR-169 | Controller Management | 30 | 30 | 0
- | PAR-170 | UI Implementation | 90 | 90 | 0
- | PAR-171 | E2E testing | 60 | 60 | 0
- | PAR-172 | Integration testing | 90 | 85 | 0.055556
- | PAR-173 | Unit testing | 60 | 60 | 0
- | PAR-174 | ENUM modification + update documentation | 30 | 60 | 1
- | PAR-175 | Router Management | 60 | 60 | 0
- | PAR-176 | Controller Management | 90 | 90 | 0
- | PAR-177 | DB config | 90 | 90 | 0
- | PAR-178 | E2E testing | 30 | 30 | 0
- | PAR-179 | Integration testing | 90 | 90 | 0
- | PAR-180 | Unit testing | 90 | 90 | 0
- | PAR-181 | UI Implementation | 60 | 120 | 1
|  |  | Estimation time | Spent time
|  | mean | 1.787 | 1.7654
|  | StDev | 2.0135 | 1.9979
|  | n | 54 | 54
|  | TotalEsitmation Error Ratio | -0.01209
|  | Absolute relative Task | 0.12027