## R1_S4
Group name | Item | Item Summary | Estimation time | Spent time | Abs Err
- | PAR-185 | Sprint planning | 12 | 12 | 0
- | PAR-186 | ISSUE: Change color of the Assign to External Maintainer button #59 | 0.16667 | 0.16667 | 0
- | PAR-187 | Scrum Meeting 1 | 1.5 | 1.5 | 0
- | PAR-188 | Scrum Meeting 2 | 1.5 | 1.5 | 0
- | PAR-189 | Scrum Meeting 3 | 1.5 | 1.5 | 0
- | PAR-190 | Scrum Meeting 4 | 1.5 | 1.5 | 0
- | PAR-192 | Technical Debt: Code Review | 5 | 5.4167 | 0.083333
- | PAR-193 | Technical Debt: Refactoring | 5 | 5.25 | 0.05
- | PAR-194 | Technical Debt: Bug Fixing | 5 | 5 | 0
- | PAR-195 | Docker Configuration | 4 | 4 | 0
- | PAR-196 | Documentation Update | 2 | 2 | 0
- | PAR-197 | Update OpenAPI Swagger | 4 | 4 | 0
- | PAR-198 | UI Implementation | 0.5 | 0.25 | 0.5
- | PAR-199 | Unit Testing | 0.5 | 0.25 | 0.5
- | PAR-200 | End to End testing | 0.5 | 0.16667 | 0.66667
- | PAR-201 | API update | 0.5 | 0.5 | 0
- | PAR-202 | UI update | 0.5 | 0.5 | 0
- | PAR-203 | Report Controller config | 1 | 1 | 0
- | PAR-204 | Integration Testing | 0.5 | 0.25 | 0.5
- | PAR-205 | Unit Testing | 0.5 | 0.41667 | 0.16667
- | PAR-206 | End to End Testing | 0.5 | 0.5 | 0
- | PAR-207 | Integration Testing | 0.5 | 0.5 | 0
- | PAR-209 | Unit Testing | 1 | 0.91667 | 0.083333
- | PAR-211 | Unit Testing | 1 | 1 | 0
- | PAR-212 | UI implementation | 1 | 1.3333 | 0.33333
- | PAR-213 | End to End Testing | 1 | 1 | 0
- | PAR-214 | Unit Testing | 1 | 0.83333 | 0.16667
- | PAR-215 | End to End Testing | 1 | 1 | 0
- | PAR-216 | End to End Testing | 1 | 0.83333 | 0.16667
- | PAR-217 | End to End Testing | 1 | 1 | 0
- | PAR-218 | End to End Testing | 1 | 1 | 0
- | PAR-219 | End to End Testing | 1 | 1 | 0
- | PAR-220 | End to End Testing | 1 | 0.75 | 0.25
- | PAR-221 | Integration Testing | 1 | 1 | 0
- | PAR-222 | Integration Testing | 1 | 1 | 0
- | PAR-223 | Integration Testing | 1 | 0.91667 | 0.083333
- | PAR-224 | UI implementation | 1 | 1.3333 | 0.33333
- | PAR-225 | UI implementation | 1 | 3 | 2
- | PAR-226 | Communication Channel Configuration | 3 | 3 | 0
- | PAR-227 | Bot Functionalities Implementation | 2 | 2 | 0
- | PAR-228 | SMTP: Email templates | 1 | 1 | 0
- | PAR-229 | Bot Functionalities Implementation | 1 | 1 | 0
- | PAR-230 | Bot Functionalities Implementation | 4 | 4 | 0
- | PAR-231 | Controller Config | 1 | 1 | 0
- | PAR-232 | Code Merge | 12 | 12 | 0
- | PAR-233 | DB Population | 1 | 1 | 0
- | PAR-234 | Version Release Testing | 1 | 1 | 0
- | PAR-235 | UI Implementation | 1.5 | 3 | 1
- | PAR-236 | End to End testing | 0.83333 | 0.5 | 0.4
- | PAR-237 | DB Config | 1 | 1 | 0
- | PAR-238 | Controller Config | 1 | 1 | 0
- | PAR-239 | Municipality Roles Update | 0.5 | 0.5 | 0
- | PAR-240 | Test Updates for Municipality Roles | 0.5 | 0.5 | 0
|  |  | Estimation time | Spent time
|  | mean | 1.8113 | 1.8601
|  | StDev | 2.3506 | 2.3945
|  | n | 53 | 53
|  | TotalEsitmation Error Ratio | 0.02691
|  | Absolute relative Task | 0.13742